## 1. Inputs Needed From You
MyGenie POS V2.4 - Inputs Needed From You
Fill the Status & Notes columns as you gather each item. P0 = blocks go-live, P1 = important, P2 = nice to have.
# | Category | What we need from you | Why / where it's used on the site | Format | Priority | Status | Your notes / link
1 | Brand | Official MyGenie logo files (light + dark versions) | Replaces the temporary text logomark in navbar & footer | SVG or transparent PNG | P0 - Blocker | Pending
2 | Brand | Exact brand hex codes & font license (if any beyond Poppins) | Confirm/lock current green #18A84A, orange #F26822, yellow #FFC529 | Doc / values | P1 - Important | Pending
3 | Pricing | Real prices for 4 plans (Starter, Growth, Pro, Chain) - monthly & annual | Pricing builder currently uses PLACEHOLDER numbers | Excel/values | P0 - Blocker | Pending
4 | Pricing | Real prices for 9 add-ons (Captain device, WhatsApp, Loyalty, Scan&Order, Delivery, Central Inv, Hotel billing, AI, Support) | Add-on cart in pricing builder | Excel/values | P0 - Blocker | Pending
5 | Pricing | Confirm what's included in each plan (feature lists) | Plan cards + 'Included/Free in plan' logic | List per plan | P1 - Important | Pending
6 | Pricing | Free trial? Setup fee? Money-back? Hardware cost? | Pricing page reassurance + FAQ | Text | P2 - Nice to have | Pending
7 | Proof | Real aggregate stats: outlets powered, cities, orders processed, total saved, avg rating | Homepage trust band + Success Stories stats (currently indicative) | Values | P0 - Blocker | Pending
8 | Proof | Approved client logos + names for the logo wall | Homepage trust marquee + customer logos | PNG/SVG logos + approval | P1 - Important | Pending
9 | Proof | Which case studies can be named publicly (sign-off) | Success Stories, sector & product proof sections | Approval list | P1 - Important | Pending
10 | Media | Feature product videos for the 5 product pages | Drops into the 'See it in action' video slot (videoUrl) | YouTube/Vimeo/MP4 links | P1 - Important | Pending
11 | Media | Real product screenshots (dashboard, KDS, captain app, room checkout, scan-order) | Replace stock images in heroes/sections | PNG/JPG | P1 - Important | Pending
12 | AI | Confirm which AI features are LIVE vs roadmap | Keeps AI copy honest (menu import, insights, upsell, validations, reporting, segmentation) | Yes/No per feature | P0 - Blocker | Pending
13 | Product | Hotel/PMS detail: standalone room billing or PMS integration? what 'single bill' covers | Hotels & Resorts page accuracy | Text | P1 - Important | Pending
14 | Product | Confirm integrations list (Swiggy, Zomato, Magicpin, Rapido, Dunzo, payments, accounting) | Cloud Kitchen page + future integrations page | List + status | P1 - Important | Pending
15 | Payments | Razorpay decision for live 'Buy Online' + keys if yes | Pricing builder checkout currently captures order only (no charge) | Yes/No + Key ID/Secret | P1 - Important | Pending
16 | Leads | Where should demo & quote leads go? (CRM / email / Google Sheet / API) | Currently saved to MyGenie DB only; needs routing to your sales | CRM name + API/email | P0 - Blocker | Pending
17 | Contact | Business phone, WhatsApp number, support email, address | Footer, contact, 'Talk to us on WhatsApp' option | Text | P1 - Important | Pending
18 | Contact | Social media links (Instagram, LinkedIn, etc.) | Footer social icons | URLs | P2 - Nice to have | Pending
19 | Legal | Privacy Policy & Terms content | Footer legal pages (required before go-live) | Text/Docs | P1 - Important | Pending
20 | GTM | Priority geographies & languages (India only? GCC? multi-language?) | Copy tone, currency, future localization | Text | P2 - Nice to have | Pending
21 | GTM | Sales reps available per sector (for sector-specific demo routing) | Sector-aware demo follow-up | Names/roles | P2 - Nice to have | Pending
22 | Deploy | Domain & DNS access to go live (e.g., mygenie.online or a subdomain) | Production deployment | Domain + DNS access | P1 - Important | Pending

## 2. Pages Built & Status
MyGenie POS V2.4 - Pages Built & Status
17 live routes. 'Uses placeholder?' shows what gets swapped once you provide the matching input from Sheet 1.
# | Page / Feature | URL (preview) | What it does | Build status | Uses placeholder?
1 | Homepage | https://pos-profit-boost.preview.emergentagent.com/ | 12 conversion sections: hero, pains, before/after, pillars, sectors, modules, AI band, proof, demo | Built & tested | Trust numbers, logo
2 | Pricing Builder | https://pos-profit-boost.preview.emergentagent.com/pricing | Recommendation quiz + 4 plans + add-on cart + upsell/cross-sell + Buy/Demo | Built & tested | Prices, payment
3 | Sector: Restaurants | https://pos-profit-boost.preview.emergentagent.com/solutions/restaurants | Pain-led sector landing + proof + FAQ + sector demo | Built & tested | Images
4 | Sector: Cafes | https://pos-profit-boost.preview.emergentagent.com/solutions/cafes | Sector landing page | Built & tested | Images
5 | Sector: QSR | https://pos-profit-boost.preview.emergentagent.com/solutions/qsr | Sector landing page | Built & tested | Images
6 | Sector: Cloud Kitchens | https://pos-profit-boost.preview.emergentagent.com/solutions/cloud-kitchens | Sector landing page | Built & tested | Images
7 | Sector: Hotels & Resorts | https://pos-profit-boost.preview.emergentagent.com/solutions/hotels-resorts | Sector landing page | Built & tested | Images
8 | Sector: Food Courts | https://pos-profit-boost.preview.emergentagent.com/solutions/food-courts | Sector landing page | Built & tested | Images
9 | Sector: Canteens & Mess | https://pos-profit-boost.preview.emergentagent.com/solutions/canteens | Sector landing page | Built & tested | Images
10 | Sector: Chains & Franchises | https://pos-profit-boost.preview.emergentagent.com/solutions/chains | Sector landing page | Built & tested | Images
11 | Product: Sell & Serve | https://pos-profit-boost.preview.emergentagent.com/product/sell-serve | Module bucket page + video slot | Built & tested | Video, images
12 | Product: Run the Property | https://pos-profit-boost.preview.emergentagent.com/product/run-property | Module bucket page + video slot | Built & tested | Video, images
13 | Product: Bring Customers Back | https://pos-profit-boost.preview.emergentagent.com/product/customers | Module bucket page + video slot | Built & tested | Video, images
14 | Product: Protect Your Profit | https://pos-profit-boost.preview.emergentagent.com/product/protect-profit | Module bucket page + video slot | Built & tested | Video, images
15 | Product: See Everything | https://pos-profit-boost.preview.emergentagent.com/product/see-everything | Module bucket page + video slot | Built & tested | Video, images
16 | Success Stories | https://pos-profit-boost.preview.emergentagent.com/customers | 15 filterable case studies + stats band | Built & tested | Aggregate stats
17 | ROI Calculator | https://pos-profit-boost.preview.emergentagent.com/roi | Live savings estimate + lead capture | Built & tested | Assumption rates
18 | Help & FAQ | https://pos-profit-boost.preview.emergentagent.com/resources | 9-question FAQ accordion | Built & tested | No
19 | Practical AI page | (not built) | Deferred per your direction - you'll share feature videos | Deferred | -

## 3. Integrations & Deploy
MyGenie POS V2.4 - Integrations & Deployment
Technical hookups pending your inputs/decisions.
# | Item | Current state | Action needed | Owner | Status
1 | Lead capture (demo form) | Saves to MyGenie database (/api/demo-request) | Decide CRM/email destination & connect | You + Dev | Pending
2 | Quote capture (pricing builder) | Saves to database (/api/quote) | Route to sales / CRM | You + Dev | Pending
3 | Online payment (Buy Online) | Captures order only - does NOT charge | Add Razorpay (provide keys) to enable real payment | You | Pending
4 | WhatsApp 'Talk to us' | Not added | Provide WhatsApp business number to add click-to-chat | You | Pending
5 | Swiggy/Zomato/Magicpin | Mentioned in copy only | Confirm live integrations; build integrations page later | You | Pending
6 | Analytics (GA4 / Meta Pixel) | Not added | Provide IDs to track conversions | You | Pending
7 | Domain & deployment | Running on preview URL | Choose domain; deploy to production | You + Dev | Pending
8 | Product videos embed | Placeholder slot ready (videoUrl=null) | Provide video links to auto-embed | You | Pending

## 4. Next Steps Roadmap
MyGenie POS V2.4 - Next Steps Roadmap
Recommended order. Complete P0 items to be go-live ready.
# | Step | Description | Depends on (from Sheet 1) | Priority | Status
1 | Swap in real prices | Replace placeholder prices in pricing builder | Items 3, 4, 5 | P0 - Blocker | Pending
2 | Swap in brand assets | Add official logo + confirm colors | Items 1, 2 | P0 - Blocker | Pending
3 | Swap in real proof | Real stats + approved logos + named case studies | Items 7, 8, 9 | P0 - Blocker | Pending
4 | Add product videos | Embed feature videos on 5 product pages | Item 10 | P1 - Important | Pending
5 | Connect leads to CRM | Route demo + quote leads to your sales system | Item 16 | P0 - Blocker | Pending
6 | Enable online payment | Wire Razorpay for live Buy Online | Item 15 | P1 - Important | Pending
7 | Add legal + contact | Privacy/Terms pages + contact details + socials | Items 17, 18, 19 | P1 - Important | Pending
8 | Add analytics | GA4 / Meta Pixel for conversion tracking | Item (analytics) | P1 - Important | Pending
9 | Build Practical AI page | When feature videos are ready | Items 10, 12 | P2 - Nice to have | Pending
10 | SEO & content | Blog/guide clusters, integrations page, comparison pages | - | P2 - Nice to have | Pending
11 | Deploy to production | Go live on your domain | Items 22 + all P0 | P1 - Important | Pending
12 | ROI report email + CRM | Email PDF savings report + pipe to CRM (suggested enhancement) | Item 16 | P2 - Nice to have | Pending

## 5. Image Mapping Plan
MyGenie POS V2.4 - Image Mapping Plan (replace ALL stock with owned assets)
Strategic plan only - no changes made yet. 43 owned images inventoried from mygenie.online. Confirm decisions, then we execute the swap.
# | Owned asset (from your live site) | What it is | Best placement in V2.4 site | Replaces (current stock) | Priority | Status | Notes / decision
1 | logo.svg (+ app/social icons) | Official MyGenie logo | Navbar + Footer | Temporary text logomark | P0 - Blocker | Pending | Use as-is
2 | banner.png (776x637) | Hero illustration | Homepage hero visual | Pexels 4339955 (owner photo) | P1 - Important | Pending | Confirm suits new hero; else use product screenshot
3 | vidban.jpg (1600x900) + YouTube video | Video banner / overview | Product page 'See it in action' slots + homepage | Empty video slot / stock hero | P1 - Important | Pending | Provide YouTube/Vimeo URL to embed
4 | feature1-5.png (300x300) | 5 feature illustrations | 5 Product page heroes + module overview | Pexels product heroes (5 photos) | P1 - Important | Pending | VERIFY what each depicts to map to correct bucket; check resolution for hero use
5 | i1-i9.svg | Feature line icons | Module/feature icons (optional) | lucide icons (already license-safe) | P2 - Nice to have | Pending | Optional - lucide is fine to keep
6 | 8 client logos (Hyatt, Bamboo Yoga, Palm Forest, Baba's Italy, Love Bites, Mill Bakery, Wild Berry, Drishti Yoga) | Brand/client logos 250x250 | Homepage trust marquee + sector 'trusted by' strips | Placeholder text logo names | P1 - Important | Pending | Confirm display rights/approval per client
7 | 11 case-study images (lovebites, ubuntu, sushi, mill, palmforest, pavandpages, terra, lafetta, beanmeup, luxevista, bambooyoga) | Case study photos/logos 250x250 | Success Stories cards + sector/product proof | Text-only cards (no image now) | P1 - Important | Pending | Map each to its matching testimonial client
8 | form-img.jpg (738x765) | Demo form side image | Demo sections (home/sector/product) | (decorative, none) | P2 - Nice to have | Pending | Optional visual
9 | apple.svg, google.svg | App Store / Play badges | Footer 'download app' | Not present | P2 - Nice to have | Pending | Add app store links
10 | youtube.png, facebook.png, mail.svg, phone1.png | Social + contact icons | Footer social + contact row | Placeholder | P1 - Important | Pending | Provide live social URLs (Sheet 1, item 18)
11 | qut.png | Quote mark graphic | Testimonial quote decoration | lucide Quote icon | P2 - Nice to have | Pending | Optional
12 | (GAP) No 8 distinct sector photos | Sector hero imagery missing | 8 Sector page heroes | Pexels sector photos (8) | P0 - Blocker | Done | RESOLVED: using brand-graphic treatment (icon + metric on deep-green panel). No photos needed.
13 | feature1-5.png mapping | Used as product-page hero illustrations (for now) | 5 Product page heroes | Pexels product photos | P1 - Important | In Progress | VERIFY each illustration matches its bucket (1=Sell&Serve, 2=Run Property, 3=Customers, 4=Protect Profit, 5=See Everything). Replace if content mismatches or low-res.
14 | Case-study image accuracy | 11 case images now on Success Stories cards | Success Stories + proof | Text-only cards | P1 - Important | In Progress | Confirm each image matches the right client; some clients have no image (initials shown): Rhino, Matryyoshka, Kates, Antonios.