## Summary
Pre-Production Checklist — Summary
Status legend: DONE · OWNER TODO · BLOCKED · READY · OPTIONAL ¦ Priority: P0 (blocker) · P1 · P2
# | Item | Owner | Status | Priority | Notes
1 | SEO | Owner+Code | READY | P0 | Build is SEO-ready; CONDITIONAL GO. Gates 1-4 must be live at DNS flip. 301 layer = single most important item.
2 | GA4 | Owner+Code | READY | P0 | Tags built & published. Remaining = mark demo_booked key event, unpause OTP tag, map values/dimensions.
3 | Meta | Owner+Code | READY | P0 | Pixel + AM on Book demo done. Remaining = replicate AM on OTP/Schedule tags, map values, verify EMQ.
4 | Google Ads | Owner+Code | READY | P0 | Tags fire on correct events. Remaining = Enhanced Conversions, demo_booked conversion from GA4, kill Zapier.
5 | Deployment | Owner+Code | READY | P0 | deployment_agent PASS. Remaining = set prod backend URL, Deploy, Calendly webhook re-register, GTM Preview verify.

## SEO
SEO Checklist
MyGenie POS — generated 2026-06-09 · container GTM-K5D84Z3L · GA4 G-KWHHFEZ5Q3 · Pixel 2862017797322752 · Ads AW-16740091756
# | Item | Owner | Status | Priority | Notes
1 | Capture Week-0 GSC baseline (indexed pages, top queries, clicks, CTR, position, current 404s) | Owner | OWNER TODO | P0 | Before DNS flip. Reference: SEO_Migration_Weekly_Monitoring_Report.md §I.
2 | Stage 301 redirect layer at Cloudflare (import frontend/cloudflare-bulk-redirects.csv as Bulk Redirect List + rule) | Owner | READY | P0 | GATE 1. 19 old→new mappings prepared & validated. Emergent managed hosting alone CANNOT do 301s — must be Cloudflare or nginx.
3 | Preserve non-www → www 301 (apex mygenie.online → https://www.mygenie.online) | Owner | READY | P0 | GATE 2. Already live on Cloudflare — keep the rule active after cutover.
4 | Confirm canonical host = https://www.mygenie.online across canonical/OG/JSON-LD | Code | DONE | P0 | Validated in build JS via SITE_URL. No mixed-host canonical.
5 | Serve sitemap.xml (48 URLs, www-only) + robots.txt at domain root | Code | DONE | P0 | Validated in build artifact. Re-confirm with curl post-cutover (preview shows Cloudflare-managed robots).
6 | Verify Google Search Console property for https://www.mygenie.online | Owner | OWNER TODO | P0 | DNS TXT or HTML tag. Submit sitemap immediately post-cutover (GATE 4).
7 | Facebook domain verification preserved in index.html | Code | DONE | P1 | 52wnu6dg7xaa18lrghxek38u535rtw present in build.
8 | Post-cutover QA: all 19 old URLs return real HTTP 301; new + 21 blog pages return 200 | Owner | OWNER TODO | P0 | Run deploy-time QA block (SEO_Production_Cutover_Gate.md §F). PASS bar before declaring SEO closed.
9 | Validate OG tags with FB Sharing Debugger + Twitter Card Validator (home + 1 blog post) | Owner | OWNER TODO | P1 | After cutover.
10 | Bing Webmaster — add property + submit sitemap | Owner | OPTIONAL | P2 | Optional.
11 | Prerender/SSR (react-snap) for empty-HTML SPA risk | Code | OPTIONAL | P1 | GATE 5 — does not block GO; schedule post-cutover.

## GA4
GA4 Checklist
MyGenie POS — generated 2026-06-09 · container GTM-K5D84Z3L · GA4 G-KWHHFEZ5Q3 · Pixel 2862017797322752 · Ads AW-16740091756
# | Item | Owner | Status | Priority | Notes
1 | GA4 base tag live via GTM (Measurement ID G-KWHHFEZ5Q3) | Code/Owner | DONE | P0 | Loaded through container GTM-K5D84Z3L; host-gated to www.mygenie.online.
2 | page_view fires on every SPA route change | Code | DONE | P0 | Verified via headless dataLayer.
3 | GA4 - Book Appointment tag on calendly Trigger (Event name demo_booked) | Owner | DONE | P0 | Created + container PUBLISHED (13 tags / 9 triggers).
4 | Mark demo_booked as a GA4 Key event (after 1 live test booking) | Owner | OWNER TODO | P0 | Then import into Google Ads as the 'Book appointment' conversion (account is GA4-linked).
5 | Unpause GA4 - OTP Verified tag (trigger lead_verifided) | Owner | OWNER TODO | P0 | Currently PAUSED. Trigger name already correct (intentional typo).
6 | Map conversion_value (+ currency INR) into GA4 conversion tags | Owner | OWNER TODO | P1 | Site sends form_submitted=₹0, lead_verified=₹500, demo_booked=₹2000.
7 | Register GA4 custom dimensions: otp_verified, form_location, plan_interest (+ optional lead_quality) | Owner | OWNER TODO | P1 | GA4 Admin → Custom definitions → event-scoped. Fields already pushed to dataLayer.
8 | Verify all events in GA4 Realtime after deploy + test booking | Owner | OWNER TODO | P0 | form_submitted → lead_verifided → thankyou_conversion → demo_booked.

## Meta
Meta Checklist
MyGenie POS — generated 2026-06-09 · container GTM-K5D84Z3L · GA4 G-KWHHFEZ5Q3 · Pixel 2862017797322752 · Ads AW-16740091756
# | Item | Owner | Status | Priority | Notes
1 | Meta Pixel base live via GTM (Pixel ID 2862017797322752) | Code/Owner | DONE | P0 | Through container GTM-K5D84Z3L.
2 | FB - Book Appointment tag (Standard event Schedule) on calendly Trigger | Owner | DONE | P0 | Created by owner.
3 | Unpause FB - OTP Verified tag (trigger lead_verifided) | Owner | DONE | P0 | Owner unpaused.
4 | Manual Advanced Matching on FB - Book demo (6 params) | Owner | DONE | P0 | Mapped first_name/last_name/phone/email/external_id(=phone)/city_name from dataLayer.
5 | Replicate the 6-row Advanced Matching block on FB - OTP Verified + Schedule tags | Owner | OWNER TODO | P0 | Code already feeds all 6 fields on every lead/booking event.
6 | Map conversion_value (+ currency INR) into Meta conversion tags | Owner | OWNER TODO | P1 | lead_verified=₹500, demo_booked=₹2000.
7 | Publish container + verify Event Match Quality (EMQ) in Events Manager Test Events | Owner | OWNER TODO | P0 | After deploy — confirm AM raises match-rate.

## Google Ads
Google Ads Checklist
MyGenie POS — generated 2026-06-09 · container GTM-K5D84Z3L · GA4 G-KWHHFEZ5Q3 · Pixel 2862017797322752 · Ads AW-16740091756
# | Item | Owner | Status | Priority | Notes
1 | Google Ads base / conversion linker live (AW-16740091756 / NtqdClejmOgaEOyOpq4-) | Code/Owner | DONE | P0 | Through container GTM-K5D84Z3L.
2 | GAds - Book Demo fires on lead_verifided (verified event) | Owner | DONE | P0 | Earlier 'repoint to lead_verified' task is MOOT — already on the verified event.
3 | Turn ON Enhanced Conversions for leads + map User-Provided Data (email/phone/first/last/city) | Owner | OWNER TODO | P0 | BIGGEST lever. Raw fields already in dataLayer; GTM hashes automatically.
4 | Create / import 'Book appointment' conversion from GA4 demo_booked key event | Owner | OWNER TODO | P0 | Existing 'Book appointments' is Import-from-clicks (Zapier) — no tag/ID/label, so use GA4 key-event import. Set Primary.
5 | Map conversion_value into Ads conversion tags; set demo_booked as value-based secondary | Owner | OWNER TODO | P1 | Confirm ₹2000 is right for a booked demo vs real avg deal value.
6 | Build junk-exclusion / suppression audience where lead_quality = junk | Owner | OWNER TODO | P2 | Stop paying to retarget bots / too-fast submits.
7 | Turn OFF the Zapier appointment import once browser demo_booked conversion is confirmed | Owner | OWNER TODO | P0 | Prevents double-counting in Google Ads. Do AFTER verifying the new conversion fires.

## Deployment
Deployment Checklist
MyGenie POS — generated 2026-06-09 · container GTM-K5D84Z3L · GA4 G-KWHHFEZ5Q3 · Pixel 2862017797322752 · Ads AW-16740091756
# | Item | Owner | Status | Priority | Notes
1 | Set REACT_APP_BACKEND_URL to the PRODUCTION backend URL before build | Owner/Code | OWNER TODO | P0 | GATE 3 (functional) — currently preview URL; would break the demo form.
2 | Keep REACT_APP_GTM_ID=GTM-K5D84Z3L in frontend/.env | Code | DONE | P0 | Re-added after env recreation. GTM is host-gated; without it NO tags fire in prod.
3 | .gitignore no longer blocks .env files from deploying | Code | DONE | P0 | Removed .env/.env.*/*.env ignore lines so backend/.env + frontend/.env ship.
4 | deployment_agent readiness check | Code | DONE | P0 | PASS. DB .to_list(1000/5000) caps deemed non-blocking admin patterns.
5 | Click Deploy (Emergent) → site live on www.mygenie.online | Owner | OWNER TODO | P0 | First time GTM actually loads (host-gated).
6 | Verify SSL green on https://www.mygenie.online | Owner | OWNER TODO | P0 | After DNS flip.
7 | Re-register Calendly webhook to the production external URL | Code | BLOCKED | P0 | Awaiting deploy. POST /api/webhooks/calendly — needed so bookings hit backend + Freshsales flow.
8 | Run GTM Preview after deploy — confirm every tag fires on its trigger | Owner | OWNER TODO | P0 | form_submitted → lead_verifided → thankyou_conversion → demo_booked.
9 | Do 1 live test booking end-to-end (form → OTP → Calendly) | Owner | OWNER TODO | P0 | Drives the GA4 key-event + Ads conversion import steps.
10 | Watch rollback triggers in first 1-24h (old URLs 404, canonical broken, blank render, 5xx) | Owner | OWNER TODO | P0 | Rollback = repoint DNS back to old origin (fast, non-destructive).
11 | Delete leftover QA/test contacts from Freshsales | Owner | OWNER TODO | P2 | e.g. 402209074834 / 402209074908 + 'Smoke Test'/'QA Tester'.